## Sprint Tracker 1
March 1st -14th |  |  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) |  |  | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 4) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 |  |  |  | Ideal
|  |  |  | Date | 2021-03-01 | 2021-03-02 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-06 | 2021-03-07 | 2021-03-08 | 2021-03-09 | 2021-03-10 | 2021-03-11 | 2021-03-12 | 2021-03-13 | 2021-03-14 |  | Dates | 80 | 80
[20 empty] | 2020-03-01 | 71 | 74.2857 | Ideal Burndown
|  |  | 80 | Remaining Work | 71 | 69 | 61 | 60 | 57 | 46 | 37 | 37 | 27 | 27 | 27 | 19 | 9 | 0 |  | 2020-03-02 | 69 | 68.5714 | Remaining Hrs (Total)
Assign Individual Functionality | Design Architecture | Vishal | 10 |  | 9 | 9 | 8 | 8 | 8 | 6 | 5 | 5 | 3 | 3 | 3 | 1 | 0 | 0 |  | 2020-03-03 | 61 | 62.8571
| Design User Interface | Vamsi | 10 |  | 8 | 8 | 7 | 7 | 7 | 5 | 4 | 4 | 2 | 2 | 2 | 1 | 0 | 0 |  | 2020-03-04 | 60 | 57.1429
| Develop Back-End Architecture | Vishal | 8 |  | 7 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 |  | 2020-03-05 | 57 | 51.4286
| Develop Front-End Structure | Sri Hari | 10 |  | 9 | 9 | 7 | 7 | 7 | 4 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 0 |  | 2020-03-06 | 46 | 45.7143
| Analyze Unit Testing | Dhanasree | 10 |  | 8 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 0 |  | 2020-03-07 | 37 | 40
| Develop Database Design | Dhanasree | 10 |  | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 2 | 0 |  | 2020-03-08 | 37 | 34.2857
| Write Documentation | Sri Hari | 10 |  | 10 | 10 | 8 | 8 | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 |  | 2020-03-09 | 27 | 28.5714
Develop Base Code | Scrum Organization | Vishal | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | 2020-03-10 | 27 | 22.8571
| User Stories and Wire Frames | Vamsi | 10 |  | 10 | 8 | 8 | 8 | 6 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 0 |  | 2020-03-11 | 27 | 17.1429
[20 empty] | 2020-03-12 | 19 | 11.4286
Team: | [19 empty] | 2020-03-13 | 9 | 5.7143
Dhanasree | 10 hours / Week | [18 empty] | 2020-03-14 | 0 | 0
Sri Hari | 10 hours / Week
Vamsi | 10 hours / Week
Vishal | 10 hours / Week
Total Available Hours During Sprint: | 80

## Sprint Tracker 2
[5 empty] | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 4) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 |  |  | Ideal
|  |  |  | Date | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | Dates | 80 | 80
[19 empty] | 2020-03-01 | 70 | 74.2857 | Ideal Burndown
|  |  | 80 | Remaining Work | 70 | 66 | 59 | 57 | 53 | 44 | 37 | 37 | 28 | 25 | 22 | 18 | 9 | 0 | 2020-03-02 | 66 | 68.5714 | Remaining Hrs (Total)
| Make changes to Database Schema | Vishal | 10 |  | 8 | 7 | 7 | 6 | 6 | 6 | 5 | 5 | 3 | 3 | 3 | 1 | 0 | 0 | 2020-03-03 | 59 | 62.8571
| Develop Front End GUI Base | Vamsi | 10 |  | 8 | 8 | 7 | 7 | 7 | 5 | 4 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 2020-03-04 | 57 | 57.1429
| Set up Backend Calls and DB Connections | Vishal | 10 |  | 7 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 2020-03-05 | 53 | 51.4286
| Develop Admin Related Pages | Sri Hari | 8 |  | 9 | 8 | 7 | 7 | 7 | 4 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 2020-03-06 | 44 | 45.7143
| Develop payment and management related Pages | Dhanasree | 10 |  | 8 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 0 | 2020-03-07 | 37 | 40
| Develop User related pages | Dhanasree | 10 |  | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 4 | 4 | 4 | 2 | 0 | 2020-03-08 | 37 | 34.2857
| Develop Dashboard for management | Sri Hari | 10 |  | 10 | 10 | 8 | 8 | 7 | 6 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 2020-03-09 | 28 | 28.5714
Develop Base Pages | Scrum Organization | SriHari | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2020-03-10 | 25 | 22.8571
| Gmap Integration | Vamsi | 10 |  | 10 | 8 | 7 | 7 | 5 | 5 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 0 | 2020-03-11 | 22 | 17.1429
[19 empty] | 2020-03-12 | 18 | 11.4286
Team: | [18 empty] | 2020-03-13 | 9 | 5.7143
Dhanasree | 10 hours / Week | [17 empty] | 2020-03-14 | 0 | 0
Sri Hari | 10 hours / Week
Vamsi | 10 hours / Week
Vishal | 10 hours / Week
Total Available Hours During Sprint: | 80

## Sprint Tracker 3
April1st -14th |  |  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 4) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | Dates |  | Ideal
|  |  |  | Date | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-01 | 80 | 80
[19 empty] | 2020-04-02 | 72 | 74.2857 | Ideal Burndown
|  |  | 80 | Remaining Work | 72 | 68 | 61 | 60 | 57 | 46 | 37 | 37 | 27 | 27 | 25 | 19 | 9 | 0 | 2020-04-04 | 68 | 68.5714 | Remaining Hrs (Total)
Develop Functionality | Backend GRPC Interface | Vishal | 10 |  | 10 | 9 | 8 | 8 | 8 | 6 | 5 | 5 | 3 | 3 | 3 | 1 | 0 | 0 | 2020-04-04 | 61 | 62.8571
| Set up Login and Logout | Vamsi | 8 |  | 9 | 8 | 7 | 7 | 7 | 5 | 4 | 4 | 2 | 2 | 2 | 1 | 0 | 0 | 2020-04-05 | 60 | 57.1429
| Set Up Proto buffs | Vishal | 10 |  | 8 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 2020-04-06 | 57 | 51.4286
| Develop Admin Dashboard | Sri Hari | 10 |  | 9 | 9 | 7 | 7 | 7 | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 2020-04-07 | 46 | 45.7143
| Develop Membership | Dhanasree | 10 |  | 8 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 0 | 2020-04-08 | 37 | 40
| Frontend Membership Page | Dhanasree | 10 |  | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 2 | 0 | 2020-04-09 | 37 | 34.2857
| Develop Admin Add,Delete Vehicle | Sri Hari | 10 |  | 9 | 9 | 8 | 8 | 8 | 8 | 5 | 5 | 4 | 4 | 4 | 4 | 1 | 0 | 2020-04-10 | 27 | 28.5714
| Scrum Organization | Vamsi | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2020-04-11 | 27 | 22.8571
| Base home and Login, Signup, Header Setup | Vamsi | 10 |  | 9 | 8 | 8 | 8 | 6 | 5 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 0 | 2020-04-12 | 27 | 17.1429
[19 empty] | 2020-04-13 | 19 | 11.4286
Team: | [18 empty] | 2020-04-14 | 9 | 5.7143
Dhanasree | 10 hours / Week | [17 empty] | 2020-04-15 | 0 | 0
Sri Hari | 10 hours / Week
Vamsi | 10 hours / Week
Vishal | 10 hours / Week
Total Available Hours During Sprint: | 80

## Sprint Tracker 4
April15th-31st |  |  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 4) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 |  |  | Ideal
|  |  |  | Date | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | Dates | 80 | 80
[19 empty] | 2020-03-01 | 72 | 74.2857 | Ideal Burndown
|  |  | 80 | Remaining Work | 72 | 66 | 59 | 56 | 53 | 44 | 37 | 36 | 28 | 25 | 22 | 18 | 9 | 0 | 2020-03-02 | 66 | 68.5714 | Remaining Hrs (Total)
| Design of Microservice and Nodejs Integration | Vishal | 10 |  | 9 | 7 | 7 | 6 | 6 | 6 | 5 | 5 | 3 | 3 | 3 | 1 | 0 | 0 | 2020-03-03 | 59 | 62.8571
| Develop User regsitration | Vamsi | 10 |  | 8 | 8 | 7 | 7 | 7 | 5 | 4 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 2020-03-04 | 56 | 57.1429
| Development of Admin and Backend Connections | Vishal | 10 |  | 8 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 0 | 2020-03-05 | 53 | 51.4286
| Development of Assign and Reassign Location | Sri Hari | 10 |  | 9 | 8 | 7 | 7 | 7 | 4 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 2020-03-06 | 44 | 45.7143
| Develop payment and management related Pages | Dhanasree | 10 |  | 8 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 0 | 2020-03-07 | 37 | 40
| Develop User related pages | Dhanasree | 10 |  | 9 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 4 | 4 | 4 | 2 | 0 | 2020-03-08 | 36 | 34.2857
| Develop Dashboard for management | Sri Hari | 10 |  | 10 | 10 | 8 | 8 | 7 | 6 | 5 | 5 | 5 | 5 | 5 | 4 | 1 | 0 | 2020-03-09 | 28 | 28.5714
Integration of 3 Layers | Scrum Organization | Dhanasree | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 2020-03-10 | 25 | 22.8571
| Development of User to Car Allocation | Vamsi | 10 |  | 9 | 8 | 7 | 6 | 5 | 5 | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 0 | 2020-03-11 | 22 | 17.1429
[19 empty] | 2020-03-12 | 18 | 11.4286
Team: | [18 empty] | 2020-03-13 | 9 | 5.7143
Dhanasree | 10 hours / Week | [17 empty] | 2020-03-14 | 0 | 0
Sri Hari | 10 hours / Week
Vamsi | 10 hours / Week
Vishal | 10 hours / Week
Total Available Hours During Sprint: | 80

## Sprint Tracker 5
May 1-9th |  |  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 4) |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
|  |  |  | Date | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09
Ideal Burndown
|  |  | 80 | Remaining Work | 72 | 68 | 59 | 56 | 53 | 44 | 37 | 36 | 30 | 0 |  | 0 | 0 | 0 | Remaining Hrs (Total)
Integration | Integration of GRPC and Node | Vishal | 10 |  | 9 | 9 | 7 | 6 | 6 | 6 | 5 | 5 | 5 | 0 |  | 0 | 0 | 0
| Deployment of Frontend, Microservices | Vamsi | 10 |  | 8 | 8 | 7 | 7 | 7 | 5 | 4 | 3 | 3 | 0 |  | 0 | 0 | 0
| Final Integaration and Bug Fixes | Vishal | 10 |  | 8 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 2 | 0 |  | 0 | 0 | 0
| Deployment of Backend | Sri Hari | 10 |  | 9 | 8 | 7 | 7 | 7 | 4 | 3 | 3 | 1 | 0 |  | 0 | 0 | 0
| Autoscaling and Documentation | Dhanasree | 10 |  | 8 | 8 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 0 |  | 0 | 0 | 0
| Integrate Membership | Dhanasree | 10 |  | 9 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 0 |  | 0 | 0 | 0
| Load Balancing and Backend Autoscaling | Sri Hari | 10 |  | 10 | 10 | 8 | 8 | 7 | 6 | 5 | 5 | 5 | 0 |  | 0 | 0 | 0
Deployment and Load Balancing | Scrum Organization and tracking | Vishal | 2 |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 |  | 0 | 0 | 0
| Load balancing of Microservices and Deployment | Vamsi | 10 |  | 9 | 8 | 7 | 6 | 5 | 5 | 4 | 4 | 3 | 0 |  | 0 | 0 | 0
Team:
Dhanasree | 10 hours / Week
Sri Hari | 10 hours / Week
Vamsi | 10 hours / Week
Vishal | 10 hours / Week
Total Available Hours During Sprint: | 80
| 80 | 80
| 72 | 70
| 68 | 60
| 59 | 50
| 56 | 40
| 44 | 30
| 37 | 20
| 36 | 10
| 30 | 0
| 0 | 0

## BurnDown Chart 1
Ideal
Dates | 80 | 80
2020-03-01 | 71 | 74.2857
2020-03-02 | 69 | 68.5714
2020-03-03 | 61 | 62.8571
2020-03-04 | 60 | 57.1429
2020-03-05 | 57 | 51.4286
2020-03-06 | 46 | 45.7143
2020-03-07 | 37 | 40
2020-03-08 | 37 | 34.2857
2020-03-09 | 27 | 28.5714
2020-03-10 | 27 | 22.8571
2020-03-11 | 27 | 17.1429
2020-03-12 | 19 | 11.4286
2020-03-13 | 9 | 5.7143
2020-03-14 | 0 | 0

## BurnDown Chart 2
Ideal
Dates | 80 | 80
2020-03-01 | 70 | 74.2857
2020-03-02 | 66 | 68.5714
2020-03-03 | 59 | 62.8571
2020-03-04 | 57 | 57.1429
2020-03-05 | 53 | 51.4286
2020-03-06 | 44 | 45.7143
2020-03-07 | 37 | 40
2020-03-08 | 37 | 34.2857
2020-03-09 | 28 | 28.5714
2020-03-10 | 25 | 22.8571
2020-03-11 | 22 | 17.1429
2020-03-12 | 18 | 11.4286
2020-03-13 | 9 | 5.7143
2020-03-14 | 0 | 0

## BurnDown Chart 3
Dates |  | Ideal
2020-04-01 | 80 | 80
2020-04-02 | 72 | 74.2857
2020-04-04 | 68 | 68.5714
2020-04-04 | 61 | 62.8571
2020-04-05 | 60 | 57.1429
2020-04-06 | 57 | 51.4286
2020-04-07 | 46 | 45.7143
2020-04-08 | 37 | 40
2020-04-09 | 37 | 34.2857
2020-04-10 | 27 | 28.5714
2020-04-11 | 27 | 22.8571
2020-04-12 | 27 | 17.1429
2020-04-13 | 19 | 11.4286
2020-04-14 | 9 | 5.7143
2020-04-15 | 0 | 0
|  | 72 | 68 | 61 | 60 | 57 | 46 | 37 | 37 | 27 | 27 | 25 | 19 | 9 | 0

## BurnDown Chart 4
Ideal
Dates | 80 | 80
2020-03-01 | 72 | 74.2857
2020-03-02 | 66 | 68.5714
2020-03-03 | 59 | 62.8571
2020-03-04 | 56 | 57.1429
2020-03-05 | 53 | 51.4286
2020-03-06 | 44 | 45.7143
2020-03-07 | 37 | 40
2020-03-08 | 36 | 34.2857
2020-03-09 | 28 | 28.5714
2020-03-10 | 25 | 22.8571
2020-03-11 | 22 | 17.1429
2020-03-12 | 18 | 11.4286
2020-03-13 | 9 | 5.7143
2020-03-14 | 0 | 0